## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog (Scrum)
| Table 1 | Product Backlog (Scrum)
Sprint Backlog 2
| Table 1 | Sprint Backlog 2
Sprint Backlog 1
| Table 1 | Sprint Backlog 1

## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | HealthMGMT:001 | Design Documentation for Backend application | Princy | Princy | Average | Low |  | RD:Health Care Management System Doc | Non-Functional |  |  |  |  | 20.5 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | HealthMGMT:002 | Test Plan | Princy | Princy | Average | Low |  | RD:Health Care Management System Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | HealthMGMT:003 | Bootstrapping the project | Princy | Princy | Simple | Low | RD:1 Application SetUp | RD:HealthCareManagementSystem_ver1 | Non-Functional |  |  |  |  | 3 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | HealthMGMT:004 | Entity Class and TableDesign and Populating the data | Princy | Princy | Complex | Low | RD2: Entity Class Design and RD3: Table Design | RD:HealthCareManagementSystem_ver2 | Functional |  |  |  |  | 7 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | HealthMGMT:005 | Add Centre, Test , Appointment and user. Perform Create, Add, Update and Delete | Princy | Princy | Complex | Low | RD 4: Making Service And Dao for Module | RD:HealthCareManagementSystem_ver3 | Functional |  |  |  |  | 13 hrs | Test Implemented Service Using Postman
5 | 6 | Work session | High | HealthMGMT:006 | Perform Approval of Appointment, Adding of Centre and Test inside it. | Princy | Princy | Complex | Low | RD7: Performe Operation | RD:HealthCareManagementSystem_ver4 | Functional |  |  |  |  | 13 hrs | Performe Customer operation using bank Employee on Postman
7 | 8
8 | 9
9 | 10
10 | 11
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | HealthMGMT:006 | Design Documentation fo Angular application | Princy | Princy | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
| 17 | Standard document | High | HealthMGMT:007 | Test Plan | Princy | Princy |  | Low | Making Components |  | Non Functional
16 | 18 | Standard document |  | HealthMGMT:008 | Design a home page having standard menus | Princy | Princy | Complex | Medium | Along with test |  | Functional
17 | 19 |  |  | HealthMGMT:009 | Implement of Components and service | Princy | Princy | Complex | Medium | Implement the Service in components |  | Functional
18 | 20 |  |  |  |  | Princy | Princy
19 | 21 |  |  |  |  | Princy | Princy
20 | 22 |  |  | HealthMGMT:010 | Testing individual parts | Princy | Princy | Complex | Medium | Test the Application using Angular and Spring boot |  | Functional
15 | 16 | Standard document | High | HealthMGMT:011 | Design Documentation fo Angular application | Princy | Princy | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
| 17 | Standard document | High | HealthMGMT:012 | Test Plan | Princy | Princy |  | Low | Making Components |  | Non Functional
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: Russell Pitts: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: Russell Pitts: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: Russell Pitts: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Russell Pitts: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Russell Pitts: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Russell Pitts: Brief description of the requirements necessary to fulfill the objective
Note on G3: Russell Pitts: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Russell Pitts: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Russell Pitts: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Russell Pitts: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Russell Pitts: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Russell Pitts: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Russell Pitts: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Russell Pitts: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Russell Pitts: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Russell Pitts: Use column for supporting comments.
Note on Q3: SueEllen Strapp: Column for defining the agreed upon acceptance criteria
Note on R3: SueEllen Strapp: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: SueEllen Strapp: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: SueEllen Strapp: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| HealthMGMT:008 | 1 | Wireframes and story boarding for each task | Princy Pandey | 2020-04-27 | 5hr | 0hr | completed | 5
|  | 2 | Routing Url List | Maneesh Kumar
|  | 3 | Data classes details
|  | 4 | Angular service
|  | 5 | Components details
|  | 6 | Detail about the security
| HealthMGMT:009 | 1 | service in Angular |  | 2020-04-28 | 3hr | 0hr | completed | 3
|  | 2 | Check data flow and mapping
| HealthMGMT:010 | 1 | Designing menu in template |  | 2020-04-29 | 5hr | 0hr | completed | 5
|  | 2 | Adding Routing details
|  | 3 | Displaying standard info or advertisement
| HealthMGMT:011 | 1 | connection between backend and frontend |  | 2020-05-30 | 6hr | 0hr | completed | 6
|  | 2 | Component sends the details to service
|  | 3 | Make url toconnect to backend with front end
|  | 4 | Check the data transfer between frontend and backend
|  | 5 | Check the operation of service is working fine with both end |  | 2020-05-31 | 3hr | 0hr | completed | 3
|  | 6 | Handling error in Frontend
| HealthMGMT:012 | 1 | Checking project is working or not handling the error and or not and verify important comment |  | 2020-05-31 | 4hr | 0hr | completed | 4
|  | 2 | Check all the written test cases and implement the backend test case |  | 2020-06-01 | 3hr | 0hr | completed | 3
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: Russell Pitts: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: SueEllen Strapp: This column is used to document the Use Case Identifier.
Note on D3: Russell Pitts: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: Russell Pitts: List the Scrum team members assigned to this task.
Note on F3: SueEllen Strapp: Column is used to document the date the task was assigned
Note on G3: Russell Pitts: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Theresa Merenkov: Adjusted estimate after the Sprint has begun
Note on I3: Theresa Merenkov: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Theresa Merenkov: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Russell Pitts: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: SueEllen Strapp: This column is used to link the requirements to any resulting modules (software).
Note on N3: SueEllen Strapp: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: SueEllen Strapp: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: SueEllen Strapp: This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | HealthMGMT:001 | 1 | Entity Class Design | Princy | 2020-04-17 | 0.125 | 0.083333 | Completed | 3
|  | 2 | Table Design | Princy | 2020-04-17 | 0.083333 | 0.083333 | Completed | 2
|  | 3 | Application Architecture | Maneesh | 2020-04-17 | 0.083333 | 0.020833 | Completed | 1
|  | 4 | Use case diagram | Kiran | 2020-04-17 | 0.083333 | 0.041667 | Completed | 1
|  | 5 | Sequence Diagram | Kiran | 2020-04-17 | 0.16667 | 0.083333 | Completed | 3
|  | 6 | Each use case detail description | Kiran | 2020-04-17 | 0.16667 | 0.083333 | Completed | 3
|  | 7 | Class Layer diagram | Maneesh | 2020-04-17 | 0.041667 | 0.041667 | Completed | 1
|  | 8 | Class Diagram | Maneesh | 2020-04-17 | 0.083333 | 0.020833 | Completed | 2
|  | 9 | Webservice URL Details | Princy | 2020-04-17 | 0.041667 | 0.041667 | Completed | 1
2 | HealthMGMT:002 | 1 | Test plan for dao, | Princy | 2020-04-20 | 0.083333 | 0.020833 | Completed | 2
|  | 2 | Test plan for service | Princy | 2020-04-20 | 0.083333 | 0.041667 | Completed | 1
|  | 3 | Test plan for webservice methods | Princy | 2020-04-20 | 0.083333 | 0.083333 | Completed | 3
3 | HealthMGMT:003 | 1 | Creating a Spring boot starter project | Maneesh | 2020-04-20 | 0.020833 | 0.020833 | Completed | 0.5
|  | 2 | Adding dependencies in Pom.xml and initializing it | Maneesh | 2020-04-20 | 0.020833 | 0.020833 | Completed | 0.5
|  | 3 | Adding server, jpa properties in application.properties | Maneesh | 2020-04-20 | 0.041667 | 0.020833 | Completed | 0.5
4 | HealthMGMT:004 | 1 | Entity Class Design | Princy | 2020-04-21 | 0.041667 | 0.041667 | Completed | 1
|  | 2 | Check tables are poulated in DB | Princy | 2020-04-21 | 0.125 | 0.083333 | Completed | 3
|  | 3 | Populate the Data | Kiran | 2020-04-21 | 0.125 | 0.083333 | Completed | 2
5 | HealthMGMT:005 | 1 | Write a JPQL query to add, delete and retrieve the centre and test details in DAO layer | Princy | 2020-04-22 | 0.083333 | 0.083333 | Completed | 2
|  | 2 | service method invoke the Dao and get the list. If list is empty throw CentreException "No Centre Found” and TestException "No Test Found” | Princy | 2020-04-22 | 0.083333 | 0.083333 | Completed | 2
|  | 3 | Service method check the id of centre and test if it already not exist otherwise throw exception | Princy | 2020-04-22 | 0.083333 | 0.083333 | Completed | 2
|  | 4 | REstController method get the centre and test details from the url path and send to service | Princy | 2020-04-22 | 0.083333 | 0.083333 | Completed | 2
6 | HealthMGMT:006 | 1 | Write the JPQL query to get the Centre and Test by centreID and testID respectively in DAO | Princy | 2020-04-23 | 0.125 | 0.125 | Completed | 2.5
|  | 2 | Write the JPQL query to get the User by User ID in DAO | Princy | 2020-04-23 | 0.125 | 0.125 | Completed | 2
|  | 3 | Write the JPQL query to get the Appointment made by User and approve it in DAO | Princy | 2020-04-23 | 0.125 | 0.083333 | Completed | 2
|  | 4 | Service checks the appointment , user made and sends the confirmation back | Princy | 2020-04-23 | 0.083333 | 0.083333 | Completed | 1.5
|  | 5 | If approved it will be showed to user | Princy | 2020-04-23 | 0.041667 | 0.041667 | Completed | 0.5
7 | HealthMGMT:007 | 1 | Applied Exceptions in all layers | Princy | 2020-04-24 | 0.125 | 0.125 | Completed | 3
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: Russell Pitts: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: SueEllen Strapp: This column is used to document the Use Case Identifier.
Note on D3: Russell Pitts: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: Russell Pitts: List the Scrum team members assigned to this task.
Note on F3: SueEllen Strapp: Column is used to document the date the task was assigned
Note on G3: Russell Pitts: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Theresa Merenkov: Adjusted estimate after the Sprint has begun
Note on I3: Theresa Merenkov: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Theresa Merenkov: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Russell Pitts: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: SueEllen Strapp: This column is used to link the requirements to any resulting modules (software).
Note on N3: SueEllen Strapp: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: SueEllen Strapp: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: SueEllen Strapp: This column is used to link the requirements/use cases to the test scenarios.